## Kanban
Phase | Feature | Owner | Status | Notes | Date updated
0 | Add .gitignore (PDFs, Office lock files) | Matthew Kuch | Done
0 | git mv original viz into apps/east-asia-2010/ | Matthew Kuch | Done | history preserved via rename detection
0 | Scaffold apps/africa-2050/ skeleton | Matthew Kuch | Done | index.html, css/, js/, data/
0 | Create landing index.html at repo root | Matthew Kuch | Done | Two-card layout linking both apps
0 | Update README.md as repo overview | Matthew Kuch | Done
0 | Update CLAUDE.md for new multi-app layout | Matthew Kuch | Done
0 | Generate ARCHITECTURE.docx + KANBAN.xlsx | Matthew Kuch | In Progress | Living docs, re-runnable via _generate_docs.py
0 | Smoke test: serve repo, verify archive still works | Matthew Kuch | Backlog
1 | Acquire Africapolis data (deprecated by pivot) | Matthew Kuch | Done | Numbers too jarring for audience; switched to UN WUP
1 | Pivot to UN WUP 2025 (city-proper, 2025–2035) | Matthew Kuch | Done | F21 + F25 + F01 from population.un.org/wup
1 | Source Africa basemap (Natural Earth GeoJSON) | Matthew Kuch | Done | 51 features at 1:110m
1 | Bundle cities as ES module (UN WUP) | Matthew Kuch | Done | ~328 African cities ≥300K
1 | Bundle country aggregates as ES module | Matthew Kuch | Done | 54 ISO3 countries
1 | Build data/_check.html QA page | Matthew Kuch | Done | Visible at /apps/africa-2050/data/_check.html
2 | Port SVG setup + global state object | Matthew Kuch | Backlog
2 | Port order() dispatcher with AbortController | Matthew Kuch | Backlog | Replaces v3 clearTimeout hack
2 | Port helpers.js (formatters, callout, stepper) | Matthew Kuch | Backlog
2 | Port barChart.js as reusable factory | Matthew Kuch | Backlog
2 | D3 v3 → v7 API translations (geo, scale, axis, event) | Matthew Kuch | Backlog
2 | Wire Continue/Back buttons + step circles | Matthew Kuch | Backlog
2 | Wire three-button mode switch (pop/land/density) | Matthew Kuch | Backlog
3 | Scene 0: introText (hero + basemap background) | Matthew Kuch | Done
3 | Scene 1: startBar (2025 vs 2035 totals) | Matthew Kuch | Done
3 | Scene 2: totalAreaMap (dual-layer dots, mode switch, hover) | Matthew Kuch | Done
3 | Scene 3: introSlope (with mini-slope teaser) | Matthew Kuch | Done
3 | Scene 4: slopeGraph (top 22 cities) | Matthew Kuch | Done
3 | Scene 5: introDotHistogram (with mini-histogram teaser) | Matthew Kuch | Done
3 | Scene 6: dotHistogram (% growth distribution) | Matthew Kuch | Done
3 | Scene 7: introUrbanScatter (with mini-scatter teaser) | Matthew Kuch | Done
3 | Scene 8: urbanPopDot (country scatter) | Matthew Kuch | Done
3 | Scene 9: finalText (hero + basemap background) | Matthew Kuch | Done
3.5 | Narration: all text moved to right panel (no chart overlap) | Matthew Kuch | Done | Tufte/Cairo/Few proximity principle
3.5 | Bridge scenes: mini-teasers added (slope/histogram/scatter) | Matthew Kuch | Done
3.5 | Stepper labels fixed via HTML/CSS (no JS positioning) | Matthew Kuch | Done
3.5 | Viewport-aware grid layout (no scrolling) | Matthew Kuch | Done
4 | Polish: favicon + OG meta tags for social sharing | Matthew Kuch | Done
4 | Polish: keyboard navigation (← → + 1/2/3 metric keys) | Matthew Kuch | Done
4 | Polish: dead-code sweep (timeline/progress helpers removed) | Matthew Kuch | Done
4 | Confirm colour palette with user | Matthew Kuch | In Progress | Muted ochre 2025 / terra 2035 — ask before deploy
4 | Cross-browser smoke test (Chrome/Firefox/Edge) | Matthew Kuch | Backlog
4 | Create new GitHub repo: bk-advisors/africa-2050 | Matthew Kuch | Backlog | Public URL: https://bk-advisors.github.io/africa-2050/
4 | git subtree split apps/africa-2050 → deploy branch | Matthew Kuch | Backlog | Extracts only the Africa viz with full history
4 | Push deploy branch to new repo + enable Pages | Matthew Kuch | Backlog | Requires user confirmation — publishes the live site